## Project Plan
Step | Day | Phase | Status | Date | Tools | Input | Output / What You See After This Step | What To Do
0 | Day 1 | Environment Setup | Completed |  | Python 3.11 + venv | Nothing | A clean folder with venv activated, Python 3.11 confirmed | Install Python 3.11, create project folder refund-agent/, run python3.11 -m venv venv, activate it (source venv/bin/activate on Mac/Linux or venv\Scripts\activate on Windows). Confirm with python --version.
1 | Day 1 | Project Structure | Completed |  | VS Code + folders | Empty project folder | A clean, organized codebase that looks professional from day one (agents/, tools/, graph/, data/, frontend/, observability/) | Create folders: agents/, tools/, graph/, data/, frontend/pages/, observability/, tests/. Add empty __init__.py in each Python package folder. Add .gitignore (venv, .env, __pycache__, *.db).
2 | Day 1 | Install Dependencies | Completed |  | pip + requirements.txt | requirements.txt file | All libraries installed, no import errors when running Python | Create requirements.txt with: fastapi, uvicorn, streamlit, langgraph, langchain, langchain-groq, langchain-community, pinecone-client, chromadb, sentence-transformers, openai, elevenlabs, sqlalchemy, mlflow, prometheus-client, python-dotenv, pydantic, pytest, ruff. Run pip install -r requirements.txt.
3 | Day 1 | API Keys Setup | Pending |  | Groq, Pinecone, HuggingFace, OpenAI (Whisper), ElevenLabs, .env | Nothing | .env file with 6 keys: GROQ_API_KEY, PINECONE_API_KEY, HF_TOKEN, OPENAI_API_KEY, ELEVENLABS_API_KEY, MLFLOW_TRACKING_URI. .env.example pushed to GitHub with empty placeholders. | Sign up free for each: 1) Groq - console.groq.com -> API Keys. 2) Pinecone - app.pinecone.io -> API Keys (free tier). 3) Hugging Face - huggingface.co/settings/tokens (for embeddings). 4) OpenAI - platform.openai.com (for Whisper STT). 5) ElevenLabs - elevenlabs.io -> Profile -> API Keys (free tier). Create .env with all keys, create .env.example with empty values. IMPORTANT: confirm .gitignore excludes .env before any commit.
4 | Day 1 | Setup LLM with Groq | Not Started |  | Groq API + LLaMA 3.3 70B | GROQ_API_KEY in .env | Terminal shows LLM response in under 2 seconds - no local server needed | Write tests/test_llm.py - import ChatGroq from langchain_groq, model='llama-3.3-70b-versatile', send a 'hello' test message, print the response. Confirms LLM connectivity before building the agent.
5 | Day 1 | Mock CRM Schema Design | Not Started |  | SQLite + SQLAlchemy | Nothing | data/crm.db created with empty tables: customers, orders, refund_history | Write data/models.py defining SQLAlchemy models: Customer (customer_id, name, email, tier), Order (order_id, customer_id, order_date, product_category, purchase_amount, shipping_status, return_window_days), RefundHistory (customer_id, refund_count, last_refund_date, fraud_flag). Run the script to create the tables.
6 | Day 1 | Seed Mock CRM Data | Not Started |  | Python (+ Faker optional) | models.py from Step 5 | data/crm.db populated with 15 customers, 50 orders, refund history | Write data/seed_data.py - insert 15 customers (5 Bronze / 5 Silver / 5 Gold), 50 orders distributed across them. Seed strategy: 5 clean refund-eligible cases, 5 edge cases (1 day past window, opened package), 5 policy-violation cases (30+ days, digital goods). Run the script, verify with a SELECT query.
7 | Day 1 | Write Refund Policy Document | Not Started |  | Markdown / Word | Nothing | data/policy.md - a realistic 3-4 page refund policy document | Draft the policy covering: time limits (30 days physical, 14 days digital, 7 days perishable), condition requirements (unopened, original packaging, receipt), category exclusions (final sale, intimate apparel, gift cards), tier-based exceptions (Gold members get +15 days), fraud prevention (max 3 refunds/year, velocity checks). Save as data/policy.md.
8 | Day 1 | Policy Chunking Pipeline | Not Started |  | LangChain Document Loaders + RecursiveCharacterTextSplitter | policy.md | A list of ~20-30 text chunks with metadata (category, time_limit) printed to console | Write data/ingest_policy.py - load policy.md with TextLoader, split with RecursiveCharacterTextSplitter(chunk_size=512, chunk_overlap=50), tag each chunk with metadata (category, time_limit) where applicable.
9 | Day 1 | Generate Embeddings & Upsert to Vector Store | Not Started |  | HuggingFace all-MiniLM-L6-v2 + Pinecone (ChromaDB fallback) | Chunks from Step 8, PINECONE_API_KEY | Pinecone index 'refund-policy' populated, local ChromaDB fallback created | Extend data/ingest_policy.py - embed chunks with HuggingFaceEmbeddings(all-MiniLM-L6-v2), create/connect the Pinecone index, upsert vectors with metadata. Also persist a local ChromaDB collection as an offline fallback in case the Pinecone free tier limit is hit.
10 | Day 1 | Test Policy Retrieval | Not Started |  | Pinecone / ChromaDB query | 5-10 test questions (e.g. 'Can I return a swimsuit?') | Console output showing the correct policy clauses retrieved for each test query | Write tests/test_retrieval.py - run 10 sample questions through the retriever, manually verify the top-3 results contain the right policy clause for each.
11 | Day 2 | Build check_refund_eligibility Tool | Not Started |  | Python function + SQLite | order_id | Function returns {eligible: bool, reason: str} for a given order | Write tools/eligibility_tool.py - query order + customer tier from SQLite, compare order_date against policy time limits (with Gold +15 day bonus applied), return an eligibility dict.
12 | Day 2 | Build query_policy_db Tool (RAG) | Not Started |  | LangChain retriever wrapper | Natural language question | Function returns top-k relevant policy clauses as text | Write tools/policy_tool.py - wrap the Pinecone/Chroma retriever from Step 9 into a callable tool function query_policy_db(question: str) -> list[str].
13 | Day 2 | Build calculate_refund_amount Tool | Not Started |  | Python function + SQLite | order_id | Function returns refund amount (full / partial / store credit) | Write tools/refund_amount_tool.py - apply business rules: full refund if within window and unopened, store credit for opened/edge cases, $0 plus a denial reason for policy violations.
14 | Day 2 | Build update_crm_status Tool | Not Started |  | Python function + SQLAlchemy | customer_id, status | CRM record updated, function returns a confirmation | Write tools/crm_tool.py - update the refund_history table (increment refund_count, set last_refund_date, set fraud_flag if the velocity limit is exceeded).
15 | Day 2 | Build escalate_to_human Tool | Not Started |  | Python function | summary, reason | A log entry / mock ticket created with the escalation summary | Write tools/escalation_tool.py - for the vertical-slice demo, write the escalation summary and reason to a JSON file or an 'escalations' table (a real ticketing system integration is not required).
16 | Day 2 | Build Tool Registry (MCP-Style) | Not Started |  | Python class | All tools from Steps 11-15 | A ToolServer class exposing all 5 tools with standardized schemas | Write tools/registry.py - define a ToolServer class with a consistent name / description / input_schema / run() pattern for each tool, mirroring an MCP-style decoupled integration. Register all 5 tools.
17 | Day 2 | Define LangGraph State Schema | Not Started |  | LangGraph + TypedDict | Nothing | A State TypedDict matching the schema in the project plan | Write graph/state.py - define the State TypedDict: customer_id, order_id, user_query, transcribed_voice_text, retrieved_policy_clauses, crm_lookup_result, eligibility_check, agent_decision, response_to_customer, reasoning_log, escalation_summary, trace_id.
18 | Day 2 | Build intake Node | Not Started |  | LangGraph node + Groq LLM | Raw user message | Parsed customer_id / order_id / intent appended to state | Write graph/nodes/intake.py - use the LLM with structured output (or regex first) to extract customer_id / order_id / intent from the user's free-text message.
19 | Day 2 | Build crm_lookup Node | Not Started |  | LangGraph node + tools from Step 11/14 | customer_id, order_id from state | crm_lookup_result populated in state | Write graph/nodes/crm_lookup.py - call get_customer_profile and get_order_details, write the results into state.
20 | Day 2 | Build policy_retrieval Node | Not Started |  | LangGraph node + query_policy_db tool | user_query, order category from state | retrieved_policy_clauses populated in state | Write graph/nodes/policy_retrieval.py - build a query from the order category/issue, call query_policy_db, store the top clauses in state.
21 | Day 2 | Build eligibility_evaluator Node | Not Started |  | LangGraph node + tools from Step 11/13 | crm_lookup_result, retrieved_policy_clauses | eligibility_check {eligible, reason, confidence} populated in state | Write graph/nodes/eligibility.py - call check_refund_eligibility and calculate_refund_amount, combine with the retrieved policy clauses to produce a confidence score.
22 | Day 2 | Build decision Node | Not Started |  | LangGraph node + Groq LLM structured output | eligibility_check, retrieved_policy_clauses | agent_decision set to APPROVE / DENY / ESCALATE with a reasoning_log entry | Write graph/nodes/decision.py - prompt the LLM to reason over eligibility + policy clauses and output a structured decision (APPROVE / DENY / ESCALATE) that cites the specific policy clause used.
23 | Day 2 | Build action Node | Not Started |  | LangGraph node + update_crm_status/escalate_to_human tools | agent_decision from state | CRM updated or escalation triggered, response_to_customer drafted | Write graph/nodes/action.py - branch on agent_decision: APPROVE/DENY -> update_crm_status + draft response; ESCALATE -> escalate_to_human with a summary.
24 | Day 2 | Build logging Node | Not Started |  | LangGraph node + MLflow/Prometheus (stub for now) | Full state | reasoning_log finalized, trace_id generated | Write graph/nodes/logging_node.py - assign a UUID trace_id, append a structured reasoning_log entry per node executed (full MLflow/Prometheus wiring happens in the Day 5 phase).
25 | Day 2 | Wire Conditional Edges | Not Started |  | LangGraph StateGraph | All nodes from Steps 18-24 | A compiled LangGraph graph object | Write graph/build_graph.py - wire nodes in sequence intake -> crm_lookup -> policy_retrieval -> eligibility_evaluator, then conditional edge: confidence > 0.9 -> decision, confidence < 0.9 OR fraud_flag -> escalate, Gold tier + borderline case -> decision (lenient). Compile the graph with graph.compile().
26 | Day 2 | Test End-to-End Agent Loop (CLI) | Not Started |  | Python script / curl | 3 sample queries (standard, violation, edge case) | Correct APPROVE / DENY / ESCALATE decisions printed with reasoning_log | Write tests/test_agent_loop.py - invoke the compiled graph with the 3 use cases from the project plan (UC-1, UC-2, UC-3), manually verify the decisions match expectations.
27 | Day 3 | Tune RAG Retrieval Accuracy | Not Started |  | LangChain + Pinecone | 10 test queries from Step 10 | At least 90% of queries retrieve the correct policy clause in the top-3 results | Adjust chunk_size/overlap, add metadata filters (category, time_limit) to retriever calls, re-run the Step 10 test suite until accuracy is acceptable.
28 | Day 3 | Add Metadata Filtering to Retriever | Not Started |  | Pinecone metadata filters | Order category (e.g. 'digital', 'apparel') | Retriever returns only chunks relevant to the order's category | Update tools/policy_tool.py to pass a metadata filter (e.g. category: order_category) into the Pinecone query so retrieval is narrower and more accurate per request.
29 | Day 4 | Scaffold FastAPI App | Not Started |  | FastAPI + Uvicorn | Compiled graph from Step 25 | uvicorn app.main:app --reload runs, /docs Swagger UI loads | Write app/main.py - create the FastAPI() instance, mount routers, add CORS middleware for the Streamlit frontend.
30 | Day 4 | Build /chat Endpoint | Not Started |  | FastAPI + LangGraph | POST body: {customer_id, message} | JSON response: {decision, response_to_customer, reasoning_log, trace_id} | Write app/routes/chat.py - POST /chat invokes the compiled graph with the user's message, returns the final state fields needed by the frontend.
31 | Day 4 | Build /health Endpoint | Not Started |  | FastAPI | None | GET /health returns {'status': 'ok'} | Write app/routes/health.py - a simple endpoint for Render uptime monitoring.
32 | Day 4 | Test FastAPI Endpoints | Not Started |  | curl / Postman | Sample chat payloads | All 3 use cases return correct decisions via HTTP | Run curl -X POST localhost:8000/chat -d '{...}' for UC-1, UC-2, UC-3, verify the responses match the Step 26 CLI results.
33 | Day 4 | Build Streamlit Customer Chat Page | Not Started |  | Streamlit | FastAPI backend running | A working chat UI at localhost:8501/customer | Write frontend/pages/customer.py - header 'AI Support - Refund Assistant', st.chat_input() for text, scrollable message history with st.chat_message().
34 | Day 4 | Add Status Indicators & Response Cards | Not Started |  | Streamlit | agent_decision from API response | Color-coded cards: green (approved), red (denied), yellow (escalated); status text shown while processing | Extend customer.py - show 'Typing... / Policy Check / CRM Lookup / Final Decision' status while waiting on the API call, then render the decision as a colored card.
35 | Day 4 | Connect Customer UI to FastAPI Backend | Not Started |  | requests / httpx | User message from chat input | A live, working end-to-end text conversation | Wire customer.py to POST to /chat, display the returned response_to_customer in the chat window. Test the full UC-1 / UC-2 / UC-3 flows live through the UI.
36 | Day 5 | Build Admin Dashboard - Real-Time Logs | Not Started |  | Streamlit + SQLite/MLflow | Trace logs from agent runs | An auto-refreshing table: trace_id, customer, decision, latency | Write frontend/pages/admin.py - query the stored trace logs (Step 24 output, persisted to a traces table), display with st.dataframe() and st.rerun() on a timer for auto-refresh.
37 | Day 5 | Build Reasoning Trace Viewer | Not Started |  | Streamlit st.expander + JSON | reasoning_log per trace | An expandable JSON view of each node's output for a selected trace | Add an expandable section per row in admin.py showing the full reasoning_log list and retrieved_policy_clauses for that trace_id.
38 | Day 5 | Build Policy Violation Alerts View | Not Started |  | Streamlit | Traces with decision == DENY | A filtered table of all denied requests with the cited policy clause | Add a filtered view in admin.py showing only DENY decisions along with the specific policy clause cited.
39 | Day 5 | Build Metrics Cards & CRM Lookup | Not Started |  | Streamlit st.metric + SQLite | All traces, customer_id search input | Cards: total requests, approval rate, avg latency, escalation rate; a searchable customer profile view | Add st.metric() cards computed from the traces table, plus a search box that looks up a customer_id and shows their full CRM profile/history.
40 | Day 5 | Integrate MLflow Tracing | Not Started |  | MLflow | Agent run data from each node | mlflow ui shows one experiment run per agent invocation with node timings | Wrap the LangGraph invocation in mlflow.start_run(), log params (trace_id, customer_id), metrics (node_execution_times, confidence_score), and artifacts (retrieved_documents, final_decision).
41 | Day 5 | Add Prometheus Metrics | Not Started |  | prometheus-client | Agent decisions, latencies | A /metrics endpoint exposing refund_requests_total, agent_decision_latency_seconds, escalation_rate, voice_pipeline_failures | Write observability/metrics.py - define Counter/Histogram/Gauge objects, increment/observe them inside the FastAPI /chat route, expose them via a /metrics endpoint for Prometheus to scrape.
42 | Day 5 | Set Up Grafana Dashboard | Not Started |  | Grafana + Prometheus data source | Prometheus /metrics endpoint | A live dashboard with 4 panels: request volume, decision distribution, P95 latency heatmap, active violations table | Run Grafana locally (Docker) or use the Grafana Cloud free tier, add Prometheus as a data source, build the 4 panels described in the project plan.
43 | Day 6 | Integrate Whisper Speech-to-Text | Not Started |  | OpenAI Whisper API (or local whisper) | Recorded audio blob | A /voice/transcribe endpoint returns transcribed text | Write app/routes/voice.py - POST /voice/transcribe accepts an audio file, calls the Whisper API, returns the transcribed text into transcribed_voice_text.
44 | Day 6 | Connect Voice Input to Agent Loop | Not Started |  | FastAPI + LangGraph | transcribed_voice_text | The same agent decision pipeline runs on voice input as on text | Route the transcribed text from Step 43 through the same /chat logic used for text input - no separate graph is needed.
45 | Day 6 | Integrate ElevenLabs Text-to-Speech | Not Started |  | ElevenLabs API v2 | response_to_customer text | An audio stream of the agent's spoken response | Write the TTS portion of app/routes/voice.py - send response_to_customer to ElevenLabs, return the audio via a FastAPI StreamingResponse for low latency.
46 | Day 6 | Build Streamlit Voice Component | Not Started |  | Streamlit st.audio_input + st.audio | Microphone recording | The customer can record a question and hear the agent's spoken reply in the browser | Add a mic button to customer.py using st.audio_input(), send the recording to /voice/transcribe -> /chat -> /voice/speak, play back the returned audio with st.audio(). Add an automatic fallback to text if voice fails.
47 | Day 6 | Cache Common TTS Phrases | Not Started |  | ElevenLabs + local cache | Common phrases ('Your refund is approved', etc.) | Pre-generated audio files reused instead of re-calling the TTS API | Pre-generate audio for the most common response phrases and cache them locally to cut latency on repeat use.
48 | Day 6 | Write Dockerfile | Not Started |  | Docker (multi-stage build) | requirements.txt, app code | docker build succeeds, image size under 1GB | Write a multi-stage Dockerfile: python:3.11-slim base -> install deps -> copy app code -> expose ports 8000 (FastAPI) and 8501 (Streamlit). Exclude dev dependencies.
49 | Day 6 | Write docker-compose.yml | Not Started |  | Docker Compose | Dockerfile from Step 48 | docker-compose up launches FastAPI + Streamlit (+ optional Grafana/Prometheus) with one command | Define services: backend (FastAPI), frontend (Streamlit), optionally prometheus and grafana containers, with a shared network and env_file pointing to .env.
50 | Day 6 | Write GitHub Actions CI/CD Pipeline | Not Started |  | GitHub Actions | Repo pushed to GitHub | A green checkmark on every push: lint passes, tests pass, Docker image builds | Write .github/workflows/ci.yml - on push: lint with ruff, run pytest (mocking LLM calls), build the Docker image, push it to GHCR.
51 | Day 6 | Deploy to Render | Not Started |  | Render + GitHub Actions deploy hook | Docker image / repo connected to Render | A live public URL for both the FastAPI backend and the Streamlit frontend | Create two Render services (or one combined container): a Web Service for FastAPI (port 8000) and a Static/Web Service for Streamlit (port 8501). Add all .env keys as Render environment variables. Wire the /health check.
52 | Day 7 | Run Full Test Suite Across CRM Profiles | Not Started |  | pytest + manual QA | All 15 CRM profiles | All 15 profiles tested with at least 3 scenarios each, results logged | Run the 3 UC scenarios (standard, violation, edge case) against each of the 15 seeded customers, confirm correct decisions and no state bleeding between concurrent requests.
53 | Day 7 | Verify Success Criteria Checklist | Not Started |  | Manual review | Working app | All 'Must-Demo' and 'Technical Validation' items from the project plan confirmed working | Walk through Section 15 of the plan: RAG retrieves real clauses (not LLM memorization), tool calling is dynamic, reasoning logs are human-readable, Docker builds in under 2 minutes, no state bleeding on concurrent requests.
54 | Day 7 | Record Loom Demo Video | Not Started |  | Loom | Working app (text + voice + admin dashboard) | A 7-10 minute video: intro, standard refund, policy violation, voice demo, code tour, reasoning logs, failure handling | Follow the script in Section 13 of the project plan: Live Demo (4-5 min) -> Code Tour (2-3 min) -> Reasoning Logs & Failure Handling (1-2 min). Practice once before recording.
55 | Day 7 | Write README | Not Started |  | Markdown | Loom link, architecture diagram, repo | A polished README.md following the structure in Section 14 of the plan | Write README sections: Overview, Live Demo, Architecture Diagram, Tech Stack, Quick Start (Docker), Project Structure, Agent Design, Tool Reference, Voice Pipeline, Observability, Testing, Deployment, License.
56 | Day 7 | Final Submission Checklist | Not Started |  | GitHub | Completed repo | Public GitHub repo, clean commit history, .env.example present, docker-compose works in one command | Verify every item in Section 17 of the project plan: public repo, README with setup instructions + architecture diagram + Loom link, .env.example with no real secrets, docker-compose.yml works, all 15 CRM profiles tested, video 7-10 min, admin dashboard auto-refreshes, voice pipeline tested with at least 3 utterances.

## Sheet1
git remote add origin https://github.com/Megha-002/AI-CustomerCareAgent

## How To Use
AI Customer Support Agent — Refund Processing System
7-Day Build Plan, broken into 57 trackable steps (Step 0-56)
How to use this tracker:
1. Work top to bottom — each step builds on the previous one.
2. Update 'Status' as you go: Not Started -> In Progress -> Completed -> Blocked.
3. Fill in 'Date' the day you complete each step.
4. Use the 'Day' column to track pace against the original 7-day timeline.
5. 'Tools' = what you need installed/signed up for. 'Input' = what you need
before you start. 'Output' = what 'done' looks like. 'What To Do' = the action.
Day color key (Project Plan tab):
Day 1 — Scaffolding, mock CRM data, policy ingestion (Steps 0-10)
Day 2 — Tool registry + LangGraph agent loop (Steps 11-26)
Day 3 — RAG retrieval tuning (Steps 27-28)
Day 4 — FastAPI backend + Streamlit customer chat (Steps 29-35)
Day 5 — Admin dashboard + MLflow/Prometheus/Grafana (Steps 36-42)
Day 6 — Voice pipeline + CI/CD + Docker + Render deploy (Steps 43-51)
Day 7 — Full testing, Loom video, README, submission checklist (Steps 52-56)